## ProjectTeam
Name | GitHub Alias
Team White | ch.bfh.bti7081.s2019.white
Yann Roth | yaroth
Lukas Zoller | lukaszoller
Elias Vihma
Nico Lieberherr | nicobfh
Marco Müller | mullm
Remo Hofmann | remohofmann

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original [h] | Effort Plan Updated [h] | Effort Actual [h] | Status
1 | Document feelings | The patient documents his feelings over the day. He may only use buttons or can add more information in text form | high | 100 | 100 | 0 | waiting
2 | Make calendar entry | The patient (or therapist) makes a calendar entry for an appointment. It is possible to make reminders for minor things like 'get out and take a walk' | medium | 50 | 50 | 0 | waiting
3 | Get activity suggestion | The app gives the patient activity suggestions if he doesn't know what to do or just wants some new ideas. | medium | 40 | 40 | 0 | waiting
4 | Edit activity suggestions | The patient (or therapist) can add new activities to the app or edit the ones already provided. | low | 20 | 20 | 0 | waiting
5 | Search self help group | The patient can search a selfhelp group in his area. | low | 40 | 40 | 0 | waiting
6 | Livechat | The app has a livechat feature. Patients and therapists can communicate over the app without seeing each other. | low | 60 | 60 | 0 | waiting
7 | Social support | Family and friend of the patient can be added as social support members. If they are worried about the patient, socail support members can leave a message in the app. | low | 20 | 20 | 0 | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original [h] | Effort Plan Updated [h] | Effort Actual | Status
1.1 | 1 | ClassDiagram | Update Class diagram, Projektstuktur erstellen | MainView, MainPresenter, MainModel | Yann |  | high | 2 |  |  | waiting
1.2 | 1 | Server Availability | Machbarkeit Server überprüfen |  | Remo |  | medium | 1 |  |  | waiting
1.3 | 1 | MainView | MainView mit 4 Buttons läuft, mit MainPresenter verbunden, Container für Views | MainView, MainPresenter, MainModel | Yann | Elias | high | 4 |  |  | waiting
1.4 | 1 | Mood | Für Mood (oberste Ebene): View, Presenter, Model erstellen und verknüpfen. | MoodView, MoodPresenter, MoodModel | Elias | Remo | high | 4 |  |  | waiting
1.5 | 1 | Settings | Für Settings: View, Presenter, Model erstellen und verknüpfen. | SettingsView, SettingsPresenter, SettingsModel | Remo | Lukas | high | 4 |  |  | waiting
1.6 | 1 | Tip | Für Tip: View, Presenter, Model erstellen und verknüpfen. | TipView, TipPresenter, TipModel | Lukas | Nico | high | 4 |  |  | waiting
1.7 | 1 | Calendar | Für Calendar: View, Presenter, Model erstellen und verknüpfen. | CalendarView, CalendarPresenter, CalendarModel | Nico | Marco | high | 4 |  |  | waiting
1.8 | 1 | HomeView | Für View: View, Presenter, Model erstellen und verknüpfen. | HomeView, HomePresenter, HomeModel | Marco | Yann | medium | 4 |  |  | waiting
1.9 | 1 | Calendar Logic | Logik in der Calendar Klasse implementieren, damit auf HomeView Kalendereintrag anzezeigt werden kann. | Calendar, CalendarEntry | Lukas | Elias | high | 4 |  |  | waiting
1.10 | 1 | HomeView fertig | HomeView fertigstellen, mit Slider, Kalendereintrag anzeigen | HomeView, Calendar, CalendarEntry | Marco | Yann | high | 4 |  |  | waiting
1.11 | 1 | MoodView fertig | MoodView1 (erste Ebene) fertig siehe UserStory | MoodView1 | Elias | Remo | medium | 4 |  |  | waiting
1.12 |  | Repository Design | Klassenarchitektur für Repository und DB erstellen | Repository, MoodModel, CalendarModel, TipModel, DB | Nico | Lukas | medium | 4 |  |  | waiting
1.13 | 1 | DB | DB aufsetzen, Interface für Repository | DB, DBInterface | Remo | Nico | medium | 4 |  |  | waiting
1.14 | 1 | Repository | Repository erstellen |  | Lukas | Marco | medium | 4 |  |  | waiting
1.15 | 1 | Repository anbinden | Repository mit Tips, Calendar, Mood verknüpfen | Repository, MoodModel, CalendarModel, TipModel | Yann | Elias | medium | 4 |  |  | waiting
55

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | £ | 190 | 180