## ProjectTeam
Name | GitHub Alias
Team White | ch.bfh.bti7081.s2019.white
Yann Roth | yaroth
Lukas Zoller | lukaszoller
Elias Vihma
Nico Lieberherr | nicobfh
Marco Müller | mullm
Remo Hofmann | remohofmann

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Document feelings | The patient documents his feelings over the day. He may only use buttons or can add more information in text form | high | 50h | 50h | 0h | waiting
2 | Make calendar entry | The patient (or therapist) makes a calendar entry for an appointment. It is possible to make reminders for minor things like 'get out and take a walk' | high | 50h | 50h | 0h | waiting
3 | Get activity suggestion | The app gives the patient activity suggestions if he doesn't know what to do or just wants some new ideas. | medium | 40h | 40h | 0h | waiting
4 | Edit activity suggestions | The patient (or therapist) can add new activities to the app or edit the ones already provided. | low | 20h | 20h | 0h | waiting
5 | Search self help group | The patient can search a selfhelp group in his area. | low | 40h | 40h | 0h | waiting
6 | Livechat | The app has a livechat feature. Patients and therapists can communicate over the app without seeing each other. | low | 60h | 60h | 0h | waiting
7 | Social support | Family and friend of the patient can be added as social support members. If they are worried about the patient, socail support members can leave a message in the app. | low | 20h | 20h | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180